## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Anurag Pareek
Document Created On: | 2024-06-17
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Project Plan
PROJECT PLAN
DOCUMENT VERSION: 1.0
PROJECT NAME | Student Placement Prediction
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Job Cloud Job Portal
PROJECT SCOPE
PROJECT START DATE | 2024-06-20
PROJECT END DATE | 2024-07-12
OVERALL PROGRESS | Completed
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem |  | 2024-06-17 | 2024-06-21 | 3 | COMPLETED
| 1.2 Recruit a team |  | 2024-06-17 | 2024-06-21 | 3 | COMPLETED
| 1.3 Create a project charter |  | 2024-06-17 | 2024-06-21 | 3 | COMPLETED
| 1.4 Requirement gathering |  | 2024-06-17 | 2024-06-21 | 3 | COMPLETED
2 Planning
| 2.1 Approval of business process |  | 2024-06-21 | 2024-06-22 | 1 | COMPLETED
| 2.2 Baseline project plan |  | 2024-06-21 | 2024-06-22 | 1 | COMPLETED
| 2.3 Team roles and responsibilities |  | 2024-06-21 | 2024-06-22 | 1 | COMPLETED
3 Execution
| 3.1 Finalize design |  |  |  | 8 | COMPLETED
| 3.2 Build |  | 2024-06-22 | 2024-06-22 | 1 | COMPLETED
| 3.2.1 Features |  | 2024-06-17 | 2024-06-22 | 9 | COMPLETED
Model Type
| Home page layout |  | 2024-06-17 | 2024-06-22 | 10 | COMPLETED
Navigation bar with logo
Home
| Jobs |  |  |  |  | COMPLETED
| Candidates |  |  |  | 1
| List of candidates with information |  |  |  |  | COMPLETED
| Employer |  | 2024-06-22 | 2024-06-23 | 1
| List of employers with information |  |  |  |  | COMPLETED
Advance search bar
Keyoword
Upload resume
Job categories
| Job listing/ Job result page |  | 2024-06-17 | 2024-06-23 | 4 | COMPLETED
| Employer name |  |  |  |  | COMPLETED
| Job category & type information |  |  |  |  | COMPLETED
| Date & location |  |  |  |  | COMPLETED
| Favorite |  |  |  |  | COMPLETED
Apply filter & sort
| Apply for job/ Jobs tag |  | 2024-06-17 | 2024-06-23 | 3 | COMPLETED
| Employer information |  |  |  |  | COMPLETED
| Deadline of application |  |  |  |  | COMPLETED
| Job details |  |  |  |  | COMPLETED
| Job description |  |  |  |  | COMPLETED
| Role |  |  |  |  | COMPLETED
Required skills
| Model Deployment |  | 16/3/2020 | 22/3/2020 | 7 | COMPLETED
| Job title and desciption |  |  |  |  | COMPLETED
| Job category and type |  |  |  |  | COMPLETED
| Required skills and application deadline |  |  |  |  | COMPLETED
| Salary and qualification |  |  |  |  | COMPLETED
Location
| 3.3 Testing |  | 2024-06-30 | 2024-07-05 | 6 | COMPLETED
3.3.1 Training & Testing Model
| 4 Closure |  | 05/07/24 | 2024-07-11 | 1 | COMPLETED